## Sheet1
ChatterTale Roll-Out Schedule
Prototype |  |  |  |  | Roll-Out
Task | Lead Team Member | Secondary | Due Date | Done | Task | Lead Team Member | Due Date | Done
Internal Components |  |  |  |  | Packaging | Ali
Order battery (define the battery) | Rodrigo |  | 2015-04-21 |  | Design packaging | Ali
Redesign PCB board | Rodrigo |  | 2015-04-28 |  | Order Stickers | Ali
Order PCB board | Rodrigo |  | 2015-05-01
Define parts (pot, speaker, buttons) | Rodrigo |  | 2015-04-21 |  | Coordinate with Library | Ali
Order internal components | Paapa/Ali |  | 2015-04-24
[5 empty] | Order Components | Rodrigo
Design Bear | Catie |  | 2015-05-15 |  | Assemble sets of electronics | Paapa/Ali
Define buttons and how to fix them | Rodrigo
Button labeling (stickers? 3D printed symbols?) | Catie |  | 2015-05-01
Define how to fix the jack | Rodrigo |  | 2015-05-01 |  | Finish ChatterTale Sets |  | 2015-06-01
Add LED low battery indicator | Rodrigo/Catie |  | 2015-05-01
Add LED power-on indicator | Rodrigo |  |  |  | Distribute electronics and 3D file to library(s) |  | 2015-06-15
Define how to fix the PBC boards | Rodrigo
Add the volume pot to 3D | Catie |  | 2015-05-01
Ears – test with microphone | Catie |  | 24-Apr
Ears – test with audio jack | Catie |  | 2015-04-24
Sketch dimensions | Catie |  | 2015-04-21
2D drawing | Catie |  | 2015-04-24
3D case outside | Catie |  | 2015-05-01
Case inside | Catie |  | 2015-05-08
Print bear | Catie |  | 2015-05-11
Final revision | Catie |  | 2015-05-15
Instructions for printing | Catie |  | 2015-05-19
Test Prototype
Coordinate with library
Test run with kids
Assess feedback