## Sheet1
ChatterTale Roll-Out Scheduel
Prototype |  |  |  | Roll-Out
Task | Lead Team Member | Due Date | Done | Task | Lead Team Member | Due Date | Done
Internal Components |  |  |  | Packaging
Order battery |  |  |  | Design packaging
Redesign pcb board |  |  |  | Order Stickers
Order pcb board
Order other parts |  |  |  | Coordinate with Library
Design Bear | Catie | 2015-05-15 |  | Order Components
Sketch dimensions | Catie | 2015-04-21 |  | Assemble sets of electronics
2D drawing | Catie | 2015-04-24
3D case outside | Catie | 2015-05-01 |  | Finish ChatterTale Sets |  | 2015-06-01
Case inside | Catie | 2015-05-08
Print bear | Catie | 2015-05-11 |  | Distribute electronics and 3D file to library(s) |  | 2015-06-15
Final revision | Catie | 2015-05-15
Instructions for printing | Catie | 2015-05-19
Test Prototype
Coordinate with library
Test run with kids
Assess feedback